## Sheet1
Program Definition | Program Benefits Delivery | Program Closure
Create Charter
Program Kick off | Execute Pg Work products | Document & review Benefits
Draft PgM Plan | Control & Monitor performance | Align with Stakeholders
Create Goverance & Pgm Schedule | Control & Monitor Costs | Perform LL & BP
Define Pg Scope | Control & Monitor Risks | Plan & execute Transition to new Pg
Estimate Program Costs | Align with project Intedependencies | Release resources and close the Pgm
Define Resources plan | Communicate with stakeholders
Perform Risk Assessment
Business Case
Formed or abstracted Business cases from projects that justify and satisfy the Company's investment of time and money to form the program. Defined & documented the known exact costs and antcipated ROI. That would include analysis and definition of resue potential, KPI & metrics, cost benefit analysis and capital budgeting methods to prove the investments.
Program Charter
Defined program charter that officially authorizes the program formally and kicking off program. That would authorize to use resources and budget to carry out the program.
Program Roadmap & Schedule
Defined program schedule that is a high level timeline for the programs with brief overview for the next few years or monhts. It could be similar to a gantt chart or PPT, it pictorially shows the program components (projects and Sub projects) in a timeline with major milestones. It provides a generic highlevel overview of the program components that will be involved with specific milestones to achieve the program’s benefits and outcomes.
Environmental Monitoring and Control
Main role as a program manager is to continually define methods and assesses , monitor & control the environment in which it operates, for example market consumer demand, legal requirements, funding, health & safety, regulatory, economic situation and political.
Program Risk Management Strategy
The risk assessment of the program is analyzed and risk management plan is devised to ensure it aligns with the risk tolerance & apetite of the business conditions.